## Daily Tasks & Deadlines
Date | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-02 | 2019-11-03 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-09 | 2019-11-10 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22 | 2019-11-23 | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12 | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | 2020-01-18 | 2020-01-19 | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25
Day | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Deadline | [5 empty] | Project - TOR Completed |  | Cloud Computing - Multiple Choice Questionare | [10 empty] | Project - TOR Completed | Project - UML diagrams Completed | [60 empty] | Cloud Computing Goal |  | Cloud Computing Soloution and Report | Arange Project Meeting/ design document Done | [32 empty] | Group TOR Submission
Module | N/A | Project |  | Project | Project | Project | Cloud Computing | [6 empty] | Project | Project | Project | Project | Project | Project | Project | [13 empty] | Project | Animation | [7 empty] | Animation | Animation | Project |  | Animation | Animation | Animation | [22 empty] | Cloud Computing | Cloud Computing | Cloud Computing | Cloud Computing | Cloud Computing | Cloud Computing | Cloud Computing | Cloud Computing | Cloud Computing | [25 empty] | Project | Project | Project | Project |  | Project | [22 empty] | Project | Project | Group Project | Project | Project
[5 empty] | Cloud Computing | [29 empty] | Project | [7 empty] | Project | [28 empty] | Project | [5 empty] | Project | Project | Project | [28 empty] | Group Project | Group Project
Task | Make Planner, Orgonise Deadlines, Prepare documents for next project meeting | TOR |  | TOR | Finish TOR - Prepare for Multiple choice Questionare | Project Meeting 11am | Prepare for Multiple choice Questionare | [6 empty] | UML Diagrams and Read Literatture to complete TOR | UML Diagrams and Read Literatture to complete TOR | UML Diagrams and Read Literatture to complete TOR |  | TOR (Bibliography, Skills, Background) UML Diagrams (for database) | TOR (Bibliography, Skills, Background) UML Diagrams (for database) | UML Diagrams (completed) Project Meeting (Ethics, TOR Aproved) | [13 empty] | Survey and Design Documentation | Work on getting up to date with animation Tasks and contact group member. Spread leaflets for questionare | [8 empty] | Create floor model & texture - Buildings models & texture | [27 empty] | Workshop Tasks and preparing for assignment, Application Functionality | Workshop Tasks, Maps API, Twitter API | Workshop Tasks, Project Design Documentation | Workshop Tasks, Maps API, Twitter API | Workshop Tasks, Maps API, Twitter API | Workshop Tasks, Maps API, Twitter API | Cloud Computing AWS Solution | Webpage | [26 empty] | Diss Layout | Diss 500w | Diss Literature Review 500w | Diss + start Group TOR | Group Meeting | Diss 500w | [22 empty] | Research for diss + Ethics Form | Diss Lit revew | Diss Lit revew | Diss Lit revew | Meeting with Yilun Shang complete Ethics form and show lit review
Status | DONE | DONE | DONE | DONE |  |  |  | DONE | [97 empty] | DONE

## Easy Glance Planner
Date | Day | Deadlines | Tasks | Task 1 | Task 2
2020-03-20 | Fri |  | Make Plan + format report | Complete | Complete
2020-03-21 | Sat |  | Report - Lit review + Download all briefs | Complete | Complete
2020-03-22 | Sun |  | Report - Design + high fidelity designs | Complete | Complete
2020-03-23 | Mon |  | Report
2020-03-24 | Tue |  | Report - Design + high fidelity designs | Complete
2020-03-25 | Wed |  | Report - Finish Lit review
2020-03-26 | Thu |  | Send Diss to supivior to check over include Ethics PDF
2020-03-27 | Fri
2020-03-28 | Sat
2020-03-29 | Sun
2020-03-30 | Mon |  | Soph Birthday - Work on report
2020-03-31 | Tue
2020-04-01 | Wed
2020-04-02 | Thu |  | Lit Review
2020-04-03 | Fri
2020-04-04 | Sat
2020-04-05 | Sun |  | Analysis
2020-04-06 | Mon
2020-04-07 | Tue
2020-04-08 | Wed
2020-04-09 | Thu
2020-04-10 | Fri
2020-04-11 | Sat
2020-04-12 | Sun
2020-04-13 | Mon
2020-04-14 | Tue
2020-04-15 | Wed
2020-04-16 | Thu
2020-04-17 | Fri
2020-04-18 | Sat
2020-04-19 | Sun
2020-04-20 | Mon | Team Project
2020-04-21 | Tue |  | Day off
2020-04-22 | Wed
2020-04-23 | Thu |  | Development - Database + Diagrams
2020-04-24 | Fri |  | Development - Login System + Report Login secutiry
2020-04-25 | Sat |  | Development - Admin User Functionality + Report Implementation
2020-04-26 | Sun
2020-04-27 | Mon
2020-04-28 | Tue
2020-04-29 | Wed
2020-04-30 | Thu
2020-05-01 | Fri | Animation
2020-05-02 | Sat |  | Weekend Off
2020-05-03 | Sun |  | Weekend Off
2020-05-04 | Mon
2020-05-05 | Tue
2020-05-06 | Wed
2020-05-07 | Thu |  | Login System + Admin Dashboard
2020-05-08 | Fri |  | Staff Login System
2020-05-09 | Sat |  | Glucose level Logging + Staff Panic button
2020-05-10 | Sun
2020-05-11 | Mon
2020-05-12 | Tue |  | staff login + Admin Dashboard
2020-05-13 | Wed
2020-05-14 | Thu
2020-05-15 | Fri
2020-05-16 | Sat
2020-05-17 | Sun
2020-05-18 | Mon
2020-05-19 | Tue
2020-05-20 | Wed
2020-05-21 | Thu |  | Diss 2000w
2020-05-22 | Fri |  | Diss 2000w | 11000
2020-05-23 | Sat |  | team project report | 11300
2020-05-24 | Sun |  | Diss 2000w - Finish analysis (2) - Finish coding standards (3.5) | 12500 |  | Complete
2020-05-25 | Mon | Team Project report | Diss 2000w - Finish design (3.1) - Abstract | 13600
2020-05-26 | Tue |  | Finish app - PDO prepare for all SQL - info screens (text to speach) | 15700 | 2100 | https://www.youtube.com/watch?v=DOtkNxmg9QY
2020-05-27 | Wed |  | AWS setup - Evaluation - Testing
2020-05-28 | Thu | Final Year Project
2020-05-29 | Fri |  | Soph Time

## Project Plan (Initial)
Total hours: 400 |  |  |  | Semester 1 | [11 empty] | Christmas |  |  | Semester 2 | [11 empty] | Easter
Project Plan | Expected Start | Expected End | Length (hours) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
Pre Project
Research project Ideas | s1w10 | s1w3 | 5 | Semester 1 1: 2; Semester 1 2: 2; Semester 1 3: 1
PID | s1w4 | s1w4 | 4 | Semester 1 4: 4
TOR | s1w5 | s1w5 | 10 | Semester 1 5: 10
Ethics Form | s1w6 | s1w6 | 2 | Semester 1 6: 2
Practical work
Designing Survey | s1w6 | s1w6 | 2 | Semester 1 6: 2
Reviewing Survey Results | s1w7 | s1w7 | 5 | Semester 1 7: 5
UML Diagrams | s1w6 | s1w6 | 10 | Semester 1 6: 10
Design Documentation | s1w7 | s1w9 | 30 | Semester 1 7: 10; Semester 1 8: 10; Semester 1 9: 10
Front-end Development | s1w8 | s1w12 | 40 | Semester 1 8: 10; Semester 1 9: 6; Semester 1 10: 10; Semester 1 11: 7; Semester 1 12: 7
MySQL Database | Cw3 | s2w1 | 20 | Christmas 3: 10; Semester 2 1: 10
PHP functionality | s2w2 | s2w3 | 20 | Semester 2 2: 10; Semester 2 3: 10
User Testing | s2w4 | s2w4 | 5 | Semester 2 4: 5
Test Plan | s2w5 | s2w5 | 15 | Semester 2 5: 5; Semester 2 6: 10
Developing Front end Knowledge | s1w6 | s1w7 | 10 | Semester 1 6: 5; Semester 1 7: 5
Developing SQL and databse Knowledge | Cw1 | Cw2 | 10 | Christmas 1: 5; Christmas 2: 5
Report
Reading Literature | s1w3 | s2w7 | 40 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Abstract | s2w9 | s2w9 | 15 | Semester 2 9: 15
Introduction | s2w8 | s2w8 | 15 | Semester 2 8: 15
Analysis | s1w10 | s1w12 | 30 | Semester 1 10: 10; Semester 1 11: 10; Semester 1 12: 10
Synthesis | s2w1 | s2w4 | 40 | Semester 2 1: 10; Semester 2 2: 10; Semester 2 3: 10; Semester 2 4: 10
Evaluation | s2w5 | s2w8 | 35 | Semester 2 5: 10; Semester 2 6: 10; Semester 2 7: 10; Semester 2 8: 5
Conclusions | s2w9 | s2w10 | 20 | Semester 2 9: 10; Semester 2 10: 10
Reviewing Paper | s1w9 | s2w12 | 10 | Semester 1 9: 2; Semester 1 12: 2; Semester 2 4: 2; Semester 2 11: 2; Semester 2 12: 2
Formatting | s1w9 | s2w10 | 7 | Semester 1 9: 2; Semester 2 10: 5
Total hours per Week: |  |  |  | 2 | 2 | 3 | 6 | 12 | 21 | 22 | 22 | 22 | 22 | 19 | 21 | 7 | 7 | 12 | 22 | 22 | 22 | 19 | 17 | 22 | 12 | 20 | 25 | 15 | 2 | 2

## Project Plan (Ongoing)
Total hours: 400 |  |  |  | Semester 1 | [11 empty] | Christmas |  |  | Semester 2 | [11 empty] | Easter
Project Plan | Expected Start | Expected End | Length (hours) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3
Pre Project
Research project Ideas | s1w10 | s1w3 | 5 | Semester 1 1: 2; Semester 1 2: 2; Semester 1 3: 1
PID | s1w4 | s1w4 | 4 | Semester 1 4: 4
TOR | s1w5 | s1w5 | 10 | Semester 1 5: 10
Ethics Form | s1w6 | s1w6 | 2 | bar: Semester 1 6; Semester 1 8
Practical work
Designing Survey | s1w6 | s1w6 | 2 | Semester 1 7: 2
Reviewing Survey Results | s1w7 | s1w7 | 5 | Semester 1 8: 5
UML Diagrams | s1w6 | s1w6 | 10 | Semester 1 6: 8; Semester 1 7: 2
Design Documentation | s1w7 | s1w9 | 30 | Semester 1 7: 10; Semester 1 8: 5; Semester 1 9: 10; Christmas 3: 5
Front-end Development | s1w8 | s1w12 | 40 | Semester 1 8: 10; Semester 1 9: 6; Semester 1 10: 10; Semester 1 11: 7; Semester 1 12: 7
MySQL Database | Cw3 | s2w1 | 20 | Christmas 3: 10; Semester 2 1: 10
PHP functionality | s2w2 | s2w3 | 20 | Semester 2 2: 10; Semester 2 3: 10
User Testing | s2w4 | s2w4 | 5 | Semester 2 4: 5
Test Plan | s2w5 | s2w5 | 15 | Semester 2 5: 5; Semester 2 6: 10
Developing Front end Knowledge | s1w6 | s1w7 | 10 | Semester 1 6: 3; Semester 1 7: 5; Semester 1 9: 2
Developing SQL and databse Knowledge | Cw1 | Cw2 | 10 | Christmas 1: 5; Christmas 2: 5
Report
Reading Literature | s1w3 | s2w7 | 40 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Abstract | s2w9 | s2w9 | 15 | Semester 2 9: 15
Introduction | s2w8 | s2w8 | 15 | Semester 2 8: 15
Analysis | s1w10 | s1w12 | 30 | Christmas 1: 10; Christmas 2: 10; Christmas 3: 10
Synthesis | s2w1 | s2w4 | 40 | Semester 2 1: 10; Semester 2 2: 10; Semester 2 3: 10; Semester 2 4: 10
Evaluation | s2w5 | s2w8 | 35 | Semester 2 5: 10; Semester 2 6: 10; Semester 2 7: 10; Semester 2 8: 5
Conclusions | s2w9 | s2w10 | 20 | Semester 2 9: 10; Semester 2 10: 10
Reviewing Paper | s1w9 | s2w12 | 10 | Semester 1 9: 2; Semester 1 12: 2; Semester 2 4: 2; Semester 2 11: 2; Semester 2 12: 2
Formatting | s1w9 | s2w10 | 7 | Semester 1 9: 2; Semester 2 10: 5
Total hours per Week: |  |  |  | 2 | 2 | 3 | 6 | 12 | 14 | 21 | 23 | 24 | 12 | 9 | 11 | 17 | 17 | 27 | 22 | 22 | 22 | 19 | 17 | 22 | 12 | 20 | 25 | 15 | 2 | 2

## data
ID | Q1. Workplace | Q2. Daily tasks | Q3. Patients | Q4. patient help | Q5. staff notification | Q6. age of staff | Q7. fast care | Q8. staff shotage | Q9. Harrasment | Q10. Comments
1 | hospital | Taking patients to the radiography room | 10 to 20 | Have pager, buzzer and on wards | Alarms | 25-40 | Agree | Strongly Agree | Agree
2 | hospital | Care of patients and medication administration | 10 to 20 | Buzzer or find me | Alarm | 16-40 | Strongly Agree | Agree | Agree
3 | hospital | medication rounds, personal care for patients, wound dressings, cannulation, iv fluid/antibiotic administration, catheterisation, observations, ward rounds, discharge planning, admissions | 20+ | Call bell system | loud buzzer makes noise until we answer the call bell | 16-64 | Strongly Agree | Agree | Strongly Agree
4 | hospital | Medicine rounds, patient care | less than 10 sometimes, more than 20 other times | get our attention or press the bedside buzzer | Hallway monnitor and sounding alarm | 25-40 | Strongly Agree | Agree | Strongly Agree
5 | care-home | Meal handling. caring of residents, bathing/take to the toilet, buzzer responses, entertainment. | less than 10 | Each resident has a personal buzzer in their rooms and buzzers in all toilets and living rooms. | buzzer alarm in corridors that inform you of room that needs assistance. | 16-64 | Neutral | Agree | Agree
6 | care-home | Helping elderly patients with day to day care | 10 to 20 | ask for assistance - alarm | We'll get around to it after higher risk residents | 41-64 | Agree | Neutral | Agree | N/A
7 | care-home | care for residents, assist everyday activites. Feed, dress, bathe. Handling medication | 5 | Buzzer in room | buzzer in the passageways | 41-64 | Neutral | Strongly Agree | Neutral
8 | care-home | Responding to buzzers, aiding personal hygeine, medication administration, overseeing patients are cared for | 10 to 20 | Buzzer in room | buzzer in hallway | 16-64 | Agree | Agree | Agree
9 | care-home | medication , bathing and personal care, respond to patient needs | 20 | Buzzer | Buzzer in hall | 16-40 | Agree | Strongly Agree | neutral
10 | care-home | Engaging with residents, feeding meals, making beds and changing, dressing residents | 10 to 15 | Buzzer in room | Alarm machine that tells you the room number in hall | 25-64 | Agree | Agree | neutral
11 | care-home | Feeding, bathing, medication administration, all round care | 10 | Buzzer in room, toilets and living area | buzzer in hall | 16-65+ | neutral | Agree | Agree
12 | Hospital | Iv fluids, oral medication administration, medical record | 15-20 | Ask for help or buzzer system, pager | Alarm | 25-64 | Strongly Agree | Strongly Agree | Agree
13 | care-home | Cream and oitment appliance, bed making, dressing, bathing, feeding, assisting in hospital trips | 15 to 20 | Buzzer system | Buzzer in hallway | 25-64 | neutral | Agree | neutral
14 | care-home | Repsonding to calls, snack and meal rounds, personal care assistance, medication | 10 | Buzzer or ask carer | Buzzer in corridoor | 25-64 | neutral | Agree | Agree
15 | care-home | Medication administration, bathing and dressing, responding to resisdents needs | 10 | Buzzer is room | Buzzer with room number in corridoor | 25-64 | Agree | Agree | neutral
16 | hospital | Patient care, hospital rounds, medical administration, engaging with patients | 20 or more | Pager, buzzer system | Alarm | 25-64 | Agree | Agree | Strongly Agree

## Data interpritation
Question | Strongly Agree | Agree | Neutral | Dissagree | Strongly Dissagree |  |  | Total
Q7. Fast care | 4 | 7 | 5 | 0 | 0 | 25% | 43.75% | 68.75%
Q8. Staff shortage | 4 | 11 | 1 | 0 | 0 | 25% | 68.75% | 93.75%
Q9. Harassment | 3 | 8 | 5 | 0 | 0 | 18.75% | 50% | 68.75%
avarage
15
15
20
15
10
15
5
15
20
17.5
10 | [6 empty] | Avarage | Highest | lowest
17.5 | [6 empty] | 14.5312 | 20+ | 5
17.5
10
10
20
| Staff Age | 16-24 | 25-40 | 41-64 | 65+
care-home | 16-64 | 1 | 1 | 1
care-home | 41-64 |  |  | 1 | 1
care-home | 41-64 |  |  | 1 | 1
care-home | 16-64 | 1 | 1 | 1
care-home | 16-40 | 1 | 1
care-home | 25-64 |  | 1 | 1
care-home | 16-65+ | 1 | 1 | 1 | 1
care-home | 25-64 |  | 1 | 1
care-home | 25-64 |  | 1 | 1
care-home | 25-64 |  | 1 | 1
| Care home | 4 | 8 | 9 | 3
hospital | 25-40 |  | 1
hospital | 16-40 | 1 | 1
hospital | 16-64 | 1 | 1 | 1
hospital | 25-40 |  | 1
hospital | 25-64 |  | 1 | 1
Hospital | 25-64 |  | 1 | 1
| Hospital | 2 | 6 | 3 | 0
| total | 6 | 14 | 12 | 3